## Executive Summary
FuseTwo E2E Automation - Status Report
Advertiser platform, management portal and API coverage. Prepared by Syed Shah, QA.
Purpose
One Playwright suite that can be pointed at dev, staging or live and run as a release gate. A green gate means no known blocker is shipping. This report states what is automated today, what is still a gap, and what the work has already found.
147 | 46 | 93
Scenarios identified across 15 modules | Scenarios automated today | Scenarios still to automate
62 | 48 | 14
Automated tests executed in the latest run | Tests passing | Tests failing (see Suite Status)
What was delivered
- One suite, three targets: dev, staging and live are selected with a single TEST_ENV switch. No file editing, no commented-out URLs.
- Release gate: 'npm run gate:staging' runs every scenario tagged as a blocker and nothing else. One command per release candidate.
- Production safety: tests that create, edit or delete real data are excluded from live runs unless explicitly enabled.
- Per-environment sign-in state, so a dev session can never be replayed against staging or live.
- Open defects are automated as tagged regression guards, kept out of the gate so they never mask a new failure.
- CI can be queued against any environment and either the full suite or the gate, from the pipeline UI.
Issues found by this work
- [High] Staging advertiser host was misidentified - Fixed
- [High] A dev URL in .env would hijack staging and prod runs - Fixed
- [High] Auth setup passed silently without credentials - Fixed
- [Medium] Back button repaints the dashboard after logout - Open
- [Medium] Payment-reminder modal causes intermittent suite failures - Fixed
- [Low] Management staging uses an untrusted internal certificate - Handled
- [High] Management tests were running against the IIS 401 page, not the portal - Fixed
- [Medium] Management spec asserts navigation that does not exist - Open

## Progress
Progress report
Work completed in this session, with how each item was verified.
Work item | Status | What was done | Verification
Multi-environment support | Done | One suite now runs against dev, staging or live via a single TEST_ENV switch. Hosts moved out of .env into committed per-environment config; sign-in state is stored per environment. | Verified on all three: correct host resolved every time, invalid value rejected.
Release gate | Done | New 'release-gate' project runs only scenarios tagged @blocker. One command per release candidate: npm run gate:staging. | 8 blocker tests wired in so far; grows with each section.
Production safety | Done | Tests that create, edit or delete real data are tagged @write and excluded from live runs unless explicitly enabled. | Confirmed: prod run reports writes=blocked.
Section 1 - Auth & Session | Done | 11 tests: form render, valid login, wrong password, account-enumeration safety, empty-form validation, credential-leak guard on the sign-in API, logout session clearing, back-button check. | 11/11 pass on dev. Stable across 28 repeat runs. 9/10 on staging - the one failure is finding F-04.
Staging brought online | Done | Corrected the advertiser staging host and handled the internal CA certificate. | Section 1 executed live against staging.
Management portal unblocked | Done | Diagnosed the 'login issue' as IIS Windows Integrated Authentication, not an app login. Chromium now single-signs-on with the Windows domain session. | 401 -> 200 on both dev and staging; portal renders signed in. CI still needs the agent account granted access.
Framework defects fixed | Done | A dev URL in .env could hijack staging/live runs; auth setup passed silently without credentials; the payment-reminder modal was only dismissed by one suite. | See findings F-02, F-03, F-05.
Scenario inventory | Done | 154 scenarios identified across 15 modules from the QA Master Report, the app navigation and the open defect list, each marked automated / partial / gap. | See the Scenario Coverage sheet.
Section 2 - Registration & onboarding | Next | Full signup and onboarding flow, including regression guards for #681, #682, #683, #685, #686, #687 and the agreement wording issues (#762, #763). | Scheduled next.
Section 3 - Dashboard | Planned | Fix the three intermittent failures using the new shared modal dismissal, then add the infinite-API-loop guards for #680 and #690. | Root cause already identified (finding F-05).

## Scenario Coverage
Scenario coverage by module
Derived from the QA Master Report coverage areas, the application navigation and the open defect list.
Module | Scenario | Type | Status | Notes
1. Auth & Session | Sign-in form renders with usable controls | Functional | Automated | @blocker @smoke
1. Auth & Session | Password stays masked after entry | Security | Automated
1. Auth & Session | Valid credentials land on dashboard | Functional | Automated | @blocker @smoke
1. Auth & Session | Wrong password rejected and grants no session | Security | Automated | @blocker
1. Auth & Session | Unknown email gives identical message (no account enumeration) | Security | Automated | @blocker @security
1. Auth & Session | Empty form flags both fields, never calls the API | Functional | Automated | @blocker
1. Auth & Session | Sign-in response carries no password / security answer | Security | Automated | @blocker @security; guards #682
1. Auth & Session | Logout clears session and locks protected routes | Security | Automated | @blocker
1. Auth & Session | Back button does not repaint dashboard after logout | Security | Automated | @security; FAILS on staging - new finding
1. Auth & Session | Suite targets the requested environment | Config | Automated | @smoke
1. Auth & Session | Session survives refresh and history navigation | Functional | Automated | Executive regression
1. Auth & Session | Forgot password is account-enumeration safe | Security | Automated | Meeting-video suite
1. Auth & Session | Geo-login from 5 countries (no 502) | Functional | Partial | Needs BrightData vars in CI
1. Auth & Session | Full password-reset round trip via emailed link | Functional | Gap | Needs mailbox API access
2. Signup / Registration | Full happy-path signup | CRUD-C | Automated | Excluded from CI (CAPTCHA)
2. Signup / Registration | CAPTCHA rejects a wrong answer | Security | Gap | Bug #681
2. Signup / Registration | Save & Submit returns no HTTP 500 | Functional | Gap | Bug #683
2. Signup / Registration | Resume API leaks no password / security answer | Security | Gap | Bug #682 - still open
2. Signup / Registration | Security-question wording has no typo | UI | Gap | Bug #685
2. Signup / Registration | 'Required field*' hides after valid input | UI | Gap | Bug #686
2. Signup / Registration | Dropdowns open downward without overlaying fields | UI | Gap | Bug #687
2. Signup / Registration | Duplicate email rejected | Validation | Gap
2. Signup / Registration | Field validation: email, phone, zip, password rules | Validation | Gap
2. Signup / Registration | Wizard back/forward preserves entered data | Functional | Gap
2. Signup / Registration | Agreement wording and $50 minimum match management | Content | Gap | Bugs #762 / #763
3. Dashboard | Authenticated dashboard loads (no signin redirect) | Functional | Automated
3. Dashboard | Publisher status and performance widgets render | Functional | Partial | Flaky - payment modal; fix pending
3. Dashboard | Browser / device / platform analytics widgets render | Functional | Partial | Flaky - payment modal; fix pending
3. Dashboard | All primary navigation links present | Functional | Partial | Flaky - payment modal; fix pending
3. Dashboard | No infinite API loop (call rate capped) | Performance | Gap | Bug #680
3. Dashboard | No error-toast flood; page stays responsive | Performance | Gap | Bug #690 - still open
3. Dashboard | Widget/date filters recalculate data | Functional | Gap
3. Dashboard | Usable at a common laptop resolution | UI | Automated
4. Programs | Create a program | CRUD-C | Automated
4. Programs | List loads with pagination and page size | CRUD-R | Gap
4. Programs | Search and status filter | CRUD-R | Gap
4. Programs | Read detail - created values persisted | CRUD-R | Gap
4. Programs | Update program and confirm after reload | CRUD-U | Gap
4. Programs | Deactivate / delete program | CRUD-D | Gap
4. Programs | Required-field and duplicate-name validation | Validation | Gap
4. Programs | Website-extraction step does not hang | Functional | Gap | Bug #760 - blocks self-serve
4. Programs | Private program shows as Private | Functional | Gap | Bug #535
4. Programs | Filter bar hidden when there are 0 programs | UI | Gap | Bug #542
4. Programs | Commission Type label styling | UI | Gap | Bug #688
4. Programs | Tracking diagnosis tool | Functional | Gap
4. Programs | Programs API contract | API | Partial | Ticket 371
4. Programs | Program defaults save and re-read | CRUD-U | Gap
4. Programs | Listing and creation entry point exposed | Functional | Automated | Executive regression
5. Campaigns | Route loads | Smoke | Automated | Navigation suite
5. Campaigns | Create campaign | CRUD-C | Gap
5. Campaigns | List / search / filter | CRUD-R | Gap
5. Campaigns | Read campaign detail | CRUD-R | Gap
5. Campaigns | Update campaign | CRUD-U | Gap
5. Campaigns | Delete / deactivate campaign | CRUD-D | Gap
5. Campaigns | Date-range and validation rules | Validation | Gap
6. Creatives | Create text link | CRUD-C | Automated
6. Creatives | Create banner with image upload | CRUD-C | Automated
6. Creatives | List and filter by type / program | CRUD-R | Gap
6. Creatives | Read a created creative | CRUD-R | Gap
6. Creatives | Update text link | CRUD-U | Gap
6. Creatives | Update banner | CRUD-U | Gap
6. Creatives | Delete creative | CRUD-D | Gap
6. Creatives | HTML / script rejected in text link | Security | Gap | Stored-XSS concern, pending logging
6. Creatives | Default auto-created creatives are editable | Functional | Gap | Bug #761
6. Creatives | Invalid image type / size rejected | Validation | Gap
6. Creatives | Required-field validation | Validation | Gap
6. Creatives | Text-link and banner workflows exposed | Functional | Automated | Executive regression
7. Coupons & Offers | Create coupon | CRUD-C | Partial | Unnamed describe block
7. Coupons & Offers | List and filter | CRUD-R | Gap
7. Coupons & Offers | Read coupon detail | CRUD-R | Gap
7. Coupons & Offers | Edit loads correct promotion type and keeps coupon code | CRUD-U | Gap | Bug #727
7. Coupons & Offers | Update coupon and confirm persisted | CRUD-U | Gap
7. Coupons & Offers | Delete coupon | CRUD-D | Gap
7. Coupons & Offers | 150-character limit enforced | Validation | Gap | Pending logging
7. Coupons & Offers | 'Please select publisher' validation | Validation | Partial
7. Coupons & Offers | Start / end date validation | Validation | Gap
8. Products / Feed | Create, import and deactivate a product feed | CRUD-CUD | Automated
8. Products / Feed | Products list and search | CRUD-R | Gap
8. Products / Feed | Read product detail | CRUD-R | Gap
8. Products / Feed | Update feed config (schedule, mapping) | CRUD-U | Gap
8. Products / Feed | Delete feed | CRUD-D | Gap
8. Products / Feed | Malformed CSV handled with a clear error | Validation | Gap
8. Products / Feed | Import status / history | Functional | Gap
8. Products / Feed | Setup / import / manage areas exposed | Functional | Automated | Executive regression
9. Publishers | Publisher list loads | Smoke | Automated | Navigation suite
9. Publishers | Search and filter by status | CRUD-R | Gap
9. Publishers | Search finds non-Approved under 'All Statuses' | CRUD-R | Gap | Bug #723
9. Publishers | Read publisher detail | CRUD-R | Gap
9. Publishers | Approve / decline an application | CRUD-U | Gap
9. Publishers | Set publisher-specific commission | CRUD-U | Gap
9. Publishers | Remove / block a publisher | CRUD-D | Gap
10. Accounting | Reconcile Sales loads current-month data | CRUD-R | Automated | Excluded from CI project
10. Accounting | Upload a bonus sale | CRUD-C | Automated | Excluded from CI project
10. Accounting | API Reconcile drawer upload contract | API | Automated | Excluded from CI project
10. Accounting | Process an existing reconciliation item | CRUD-U | Automated | Excluded from CI project
10. Accounting | Reject / reverse a sale | CRUD-U | Gap
10. Accounting | 'Publishers' count not inflated | Data | Gap | Pending logging
10. Accounting | Sales-value maths reconciles (sum = total) | Data | Gap
10. Accounting | Invoices / payment history | CRUD-R | Gap
10. Accounting | Data and safe operational controls exposed | Functional | Automated | Executive regression
11. Reporting | Sales Summary: load, dates, sort, filter, columns, export | CRUD-R | Automated | 6 tests
11. Reporting | Sales Detailed: load, dates, sort, filter, columns, export | CRUD-R | Automated | 6 tests
11. Reporting | Clicks Summary: filters, sort, columns, reset, export | CRUD-R | Automated | 10 tests
11. Reporting | Clicks Detailed: load, dates, sort, filter, columns, export | CRUD-R | Automated | 6 tests
11. Reporting | Performance: custom range, last month, comparison | CRUD-R | Automated | 3 tests
11. Reporting | Performance Report returns data for a period with data | Data | Gap | Bug #726 - still open
11. Reporting | Sales Summary shows data when sales exist | Data | Gap | Bug #726 - still open
11. Reporting | Cross-report totals agree (summary = sum of detail) | Data | Gap
11. Reporting | Performance filters and report actions exposed | Functional | Automated | Executive regression
12. Message Center | Create, send and approve a message | CRUD-CU | Automated | Excluded from CI project
12. Message Center | Inbox list / read a message | CRUD-R | Gap
12. Message Center | Update a draft | CRUD-U | Gap
12. Message Center | Delete a message | CRUD-D | Gap
12. Message Center | Attachment upload | Functional | Gap
13. Settings & Support | My Account route loads | Smoke | Automated | Navigation suite
13. Settings & Support | Read profile values | CRUD-R | Gap
13. Settings & Support | Update profile and confirm after reload | CRUD-U | Gap
13. Settings & Support | Change password then sign in again | CRUD-U | Gap
13. Settings & Support | Sub-user add / edit / delete | CRUD-CUD | Gap
13. Settings & Support | Notification preferences update | CRUD-U | Gap
13. Settings & Support | Help Desk: create ticket, list, read | CRUD-CR | Gap
13. Settings & Support | Terms page renders (no blank / 500) | Functional | Gap | Bug #725
13. Settings & Support | Privacy Policy renders with real dates | Content | Gap
14. Management portal | Windows SSO gets past the IIS 401 challenge | Access | Automated | Fixed today; CI needs agent account access
14. Management portal | Loads without auth or server error | Smoke | Automated
14. Management portal | Nav exposes the real Advertiser / Reports sections | Functional | Partial | Existing assertions are wrong - F-08
14. Management portal | Milo AI Agents page makes no failed API calls | Functional | Automated
14. Management portal | Advertiser Overview: revenue tile and status filter counts | CRUD-R | Gap
14. Management portal | Accounting: revenue, receivables, balance, invoice totals | Data | Gap
14. Management portal | Promo codes create / read / update / delete | CRUD-CRUD | Gap
14. Management portal | Referred and recruited publisher lists | CRUD-R | Gap
14. Management portal | Advertiser Detail is not 'Coming Soon' | Functional | Gap | Bug #684 - 31 approvals blocked
14. Management portal | Advertiser search and status filter | CRUD-R | Gap
14. Management portal | Advertiser approve / reject | CRUD-U | Gap
14. Management portal | Pricing Schedule matches the advertiser agreement | Data | Gap | Bug #762
14. Management portal | No legacy FlexOffers.com branding | Content | Gap | Bug #764
14. Management portal | Advertiser Details Programs workflow exposed | Functional | Automated | Ticket 371
15. Cross-cutting | 12 routes load without auth redirect or 5xx | Smoke | Automated | Navigation suite
15. Cross-cutting | Critical APIs: status, latency and schema | API | Automated
15. Cross-cutting | Unauthenticated API call rejected | Security | Automated
15. Cross-cutting | Unauthenticated dashboard access blocked | Security | Automated
15. Cross-cutting | No broken same-origin assets | Functional | Automated
15. Cross-cutting | Console-error / failed-request guard on every page | Quality | Gap
15. Cross-cutting | Reusable API-call-rate (infinite loop) detector | Performance | Gap | Would cover #680 / #690
15. Cross-cutting | XSS / HTML-injection guard across text inputs | Security | Gap
15. Cross-cutting | Dark-mode contrast and readability | UI | Gap | Bugs #452 / #449
15. Cross-cutting | Responsive: mobile and tablet on key pages | UI | Gap | Item #220
Rollup by module
Module | Automated | Partial | Gap | Total
1. Auth & Session | 12 | 1 | 1 | 14
2. Signup / Registration | 1 | 0 | 10 | 11
3. Dashboard | 2 | 3 | 3 | 8
4. Programs | 2 | 1 | 12 | 15
5. Campaigns | 1 | 0 | 6 | 7
6. Creatives | 3 | 0 | 9 | 12
7. Coupons & Offers | 0 | 2 | 7 | 9
8. Products / Feed | 2 | 0 | 6 | 8
9. Publishers | 1 | 0 | 6 | 7
10. Accounting | 5 | 0 | 4 | 9
11. Reporting | 6 | 0 | 3 | 9
12. Message Center | 1 | 0 | 4 | 5
13. Settings & Support | 1 | 0 | 8 | 9
14. Management portal | 4 | 1 | 9 | 14
15. Cross-cutting | 5 | 0 | 5 | 10
TOTAL | 46 | 8 | 93 | 147

## Suite Status
Every automated test and its latest result
Parsed directly from the Playwright run log - these are real results, not estimates.
Spec file | Test | Project | Result
Auth/auth.setup.ts | Authenticate With Advertiser Max Login (dev) | setup | PASS
Auth/testLoginPage.spec.ts | Authentication - Login page › renders the complete sign-in form with usable controls @blocker @smoke | chromium | PASS
Auth/testLoginPage.spec.ts | Authentication - Login page › does not expose a password after it is entered | chromium | PASS
Auth/testLoginPage.spec.ts | Authentication - Login page › valid credentials sign in and land on the dashboard @blocker @smoke | chromium | PASS
Auth/testLoginPage.spec.ts | Authentication - Login page › rejects a wrong password and grants no session @blocker | chromium | PASS
Auth/testLoginPage.spec.ts | Authentication - Login page › gives the same message for an unknown email as for a wrong password @blocker @security | chromium | PASS
Auth/testLoginPage.spec.ts | Authentication - Login page › flags both fields as required when the form is submitted empty @blocker | chromium | PASS
Auth/testLoginPage.spec.ts | Authentication - Login page › sign-in response never carries a password or security answer @blocker @security | chromium | PASS
Auth/testLoginPage.spec.ts | Authentication - Login page › logging out clears the session and locks protected routes @blocker | chromium | PASS
Auth/testLoginPage.spec.ts | Authentication - Login page › the back button does not repaint the dashboard after logout @security | chromium | PASS
Auth/testLoginPage.spec.ts | Authentication - environment wiring › the suite is pointed at the environment it was asked for @smoke | chromium | PASS
Creatives/testAddBanner.spec.ts | Creatives - Banner Flow › Verify user can create a Banner Creative (2.0m) | chromium | FAIL
Creatives/testAddTextLink.spec.ts | Creatives - Text Link Flow › Verify user can create a Text Link Creative (2.0m) | chromium | FAIL
Dashboard/testDashboard.spec.ts | Dashboard › loads the authenticated dashboard instead of redirecting to sign in | chromium | FAIL
Dashboard/testDashboard.spec.ts | Dashboard › shows publisher status and performance widgets | chromium | PASS
Dashboard/testDashboard.spec.ts | Dashboard › shows browser, device, and platform analytics widgets | chromium | FAIL
Dashboard/testDashboard.spec.ts | Dashboard › exposes all primary advertiser navigation links | chromium | FAIL
ExecutiveRegression/testCriticalApis.spec.ts | @executive @regression critical API health › Dashboard APIs return successful, timely, valid responses | chromium | PASS
ExecutiveRegression/testCriticalApis.spec.ts | @executive @regression critical API health › Programs APIs return successful, timely, valid responses | chromium | PASS
ExecutiveRegression/testCriticalApis.spec.ts | @executive @regression critical API health › Creatives APIs return successful, timely, valid responses | chromium | PASS
ExecutiveRegression/testCriticalApis.spec.ts | @executive @regression critical API health › Products APIs return successful, timely, valid responses | chromium | PASS
ExecutiveRegression/testCriticalApis.spec.ts | @executive @regression critical API health › Reconcile Sales APIs return successful, timely, valid responses | chromium | PASS
ExecutiveRegression/testCriticalApis.spec.ts | @executive @regression critical API health › Performance APIs return successful, timely, valid responses | chromium | PASS
ExecutiveRegression/testCriticalApis.spec.ts | @executive @regression critical API health › an API used by the dashboard rejects an unauthenticated browser | chromium | PASS
ExecutiveRegression/testDetailedFeatures.spec.ts | @executive @regression detailed feature surfaces › Programs exposes its listing and program creation entry point | chromium | PASS
ExecutiveRegression/testDetailedFeatures.spec.ts | @executive @regression detailed feature surfaces › Creatives exposes text-link and banner workflows | chromium | PASS
ExecutiveRegression/testDetailedFeatures.spec.ts | @executive @regression detailed feature surfaces › Products exposes setup, import, and management areas | chromium | PASS
ExecutiveRegression/testDetailedFeatures.spec.ts | @executive @regression detailed feature surfaces › Reconcile Sales exposes data and safe operational controls | chromium | PASS
ExecutiveRegression/testDetailedFeatures.spec.ts | @executive @regression detailed feature surfaces › Performance report exposes filters and report actions | chromium | PASS
ExecutiveRegression/testExecutiveRegression.spec.ts | @executive @regression CEO demo readiness › authenticated session survives refresh and browser history navigation | chromium | PASS
ExecutiveRegression/testExecutiveRegression.spec.ts | @executive @regression CEO demo readiness › primary menu destinations are correctly wired | chromium | PASS
ExecutiveRegression/testExecutiveRegression.spec.ts | @executive @regression CEO demo readiness › critical pages return successful documents and no broken same-origin assets | chromium | PASS
ExecutiveRegression/testExecutiveRegression.spec.ts | @executive @regression CEO demo readiness › dashboard remains usable at a common laptop resolution | chromium | FAIL
ExecutiveRegression/testExecutiveRegression.spec.ts | @executive @regression access protection › unauthenticated visitors cannot open the advertiser dashboard | chromium | PASS
MeetingVideoRegression/AdvertiserPlatform/testPasswordReset.spec.ts | @meeting-video advertiser password reset › Forgot password follows the account-enumeration-safe flow shown in the meeting | chromium | PASS
MeetingVideoRegression/AdvertiserPlatform/testPasswordReset.spec.ts | @meeting-video advertiser password reset › password remains masked after returning to sign in | chromium | PASS
MeetingVideoRegression/Management/testManagementReadOnly.spec.ts | @meeting-video Management read-only flows › Management loads without an authentication or server error | chromium | PASS
MeetingVideoRegression/Management/testManagementReadOnly.spec.ts | @meeting-video Management read-only flows › meeting navigation exposes Dashboard, Advertisers, Accounting, and Reports | chromium | FAIL
MeetingVideoRegression/Management/testManagementReadOnly.spec.ts | @meeting-video Management read-only flows › Milo AI Agents page does not produce failed API calls | chromium | PASS
Navigation/testAuthenticatedNavigation.spec.ts | Authenticated navigation › Programs route loads without an auth redirect or server error | chromium | PASS
Navigation/testAuthenticatedNavigation.spec.ts | Authenticated navigation › Campaigns route loads without an auth redirect or server error | chromium | PASS
Navigation/testAuthenticatedNavigation.spec.ts | Authenticated navigation › Creatives route loads without an auth redirect or server error | chromium | PASS
Navigation/testAuthenticatedNavigation.spec.ts | Authenticated navigation › Coupons & Offers route loads without an auth redirect or server error | chromium | PASS
Navigation/testAuthenticatedNavigation.spec.ts | Authenticated navigation › Products route loads without an auth redirect or server error | chromium | PASS
Navigation/testAuthenticatedNavigation.spec.ts | Authenticated navigation › Publisher List route loads without an auth redirect or server error | chromium | PASS
Navigation/testAuthenticatedNavigation.spec.ts | Authenticated navigation › Reconcile Sales route loads without an auth redirect or server error | chromium | PASS
Navigation/testAuthenticatedNavigation.spec.ts | Authenticated navigation › Performance route loads without an auth redirect or server error | chromium | PASS
Navigation/testAuthenticatedNavigation.spec.ts | Authenticated navigation › Sales Summary route loads without an auth redirect or server error | chromium | PASS
Navigation/testAuthenticatedNavigation.spec.ts | Authenticated navigation › Clicks Detailed route loads without an auth redirect or server error | chromium | PASS
Navigation/testAuthenticatedNavigation.spec.ts | Authenticated navigation › My Account route loads without an auth redirect or server error | chromium | PASS
Navigation/testAuthenticatedNavigation.spec.ts | Authenticated navigation › Help Desk route loads without an auth redirect or server error | chromium | PASS
Programs/testCreateProgram.spec.ts | Program Creation Flow › Verify user can create a program (2.0m) | chromium | FAIL
Programs/testProductFeed.spec.ts | Product Feed Tests › Create, Import, and Deactivate Product Feed (2.0m) | chromium | FAIL
Reporting/ClickDetailsReports.spec.ts | Reporting - Clicks Detailed › Verify Clicks Detailed page loads with table and export button visible | chromium | PASS
Reporting/ClickDetailsReports.spec.ts | Reporting - Clicks Detailed › Verify user can select a custom date range on Clicks Detailed | chromium | PASS
Reporting/ClickDetailsReports.spec.ts | Reporting - Clicks Detailed › Verify user can sort Clicks Detailed report by Program Name, Click ID and Publisher ID (2.0m) | chromium | FAIL
Reporting/ClickDetailsReports.spec.ts | Reporting - Clicks Detailed › Verify user can apply alt value filter on Clicks Detailed | chromium | PASS
Reporting/ClickDetailsReports.spec.ts | Reporting - Clicks Detailed › Verify user can add and remove columns via column visibility panel (2.0m) | chromium | FAIL
Reporting/ClickDetailsReports.spec.ts | Reporting - Clicks Detailed › Verify user can export Clicks Detailed report and file downloads (2.0m) | chromium | FAIL
Reporting/testClickSummary.spec.ts | Reporting - Clicks Summary › Verify Clicks Summary page loads with summary cards, chart and table (2.0m) | chromium | FAIL
Reporting/testClickSummary.spec.ts | Reporting - Clicks Summary › Verify user can filter Clicks Summary by Program (2.0m) | chromium | FAIL
Reporting/testClickSummary.spec.ts | Reporting - Clicks Summary › Verify user can filter Clicks Summary by Category | chromium | PASS
Total | 62 tests: 48 passed, 14 failed, 0 skipped
Rollup by spec file
Spec file | Passed | Failed | Total
Auth/auth.setup.ts | 1 | 0 | 1
Auth/testLoginPage.spec.ts | 10 | 0 | 10
Creatives/testAddBanner.spec.ts | 0 | 1 | 1
Creatives/testAddTextLink.spec.ts | 0 | 1 | 1
Dashboard/testDashboard.spec.ts | 1 | 3 | 4
ExecutiveRegression/testCriticalApis.spec.ts | 7 | 0 | 7
ExecutiveRegression/testDetailedFeatures.spec.ts | 5 | 0 | 5
ExecutiveRegression/testExecutiveRegression.spec.ts | 4 | 1 | 5
MeetingVideoRegression/AdvertiserPlatform/testPasswordReset.spec.ts | 2 | 0 | 2
MeetingVideoRegression/Management/testManagementReadOnly.spec.ts | 2 | 1 | 3
Navigation/testAuthenticatedNavigation.spec.ts | 12 | 0 | 12
Programs/testCreateProgram.spec.ts | 0 | 1 | 1
Programs/testProductFeed.spec.ts | 0 | 1 | 1
Reporting/ClickDetailsReports.spec.ts | 3 | 3 | 6
Reporting/testClickSummary.spec.ts | 1 | 2 | 3

## Findings
Issues found while building the automation
Separate from the product bugs already on the board. Each was reproduced before being recorded.
ID | Severity | Title | Area | What happens | Why it matters | Status
F-01 | High | Staging advertiser host was misidentified | Environment / config | advertiser.stg.fusetwo.com resolves to the management box (cert CN management.stg.fusetwo.com) and returns HTTP 404. The advertiser staging app is advertiserstg.fusetwo.com. | Any staging automation pointed at the obvious-looking host would have failed at connection time, or worse, silently tested the wrong system. | Fixed - config/env/staging.env now uses the verified host.
F-02 | High | A dev URL in .env would hijack staging and prod runs | Environment / config | The suite read the target host from .env, which pinned URL to the dev sign-in page. Selecting another environment could not override it. | A 'staging run' would have silently exercised dev and reported green. | Fixed - hosts now come from config/env/<env>.env and are applied over .env.
F-03 | High | Auth setup passed silently without credentials | Test framework | auth.setup.ts wrapped its login in a type guard; with FO_USERNAME/FO_PASSWORD unset it wrote an anonymous storage state and reported success. | Every dependent test then failed for a misleading reason instead of one clear error. | Fixed - credentials are required and the dashboard landing is asserted.
F-04 | Medium | Back button repaints the dashboard after logout | Advertiser portal - session | After logout the session is genuinely cleared (a direct hit on /app/dashboard redirects to sign-in), but pressing Back restores the dashboard URL and its rendered page from the back-forward cache without re-running the route guard. | Account data stays visible after sign-out on a shared machine. Not an auth bypass - API calls are unauthenticated. | Open - reproduced on staging (advertiserstg) on 20 Aug 2026; dev redirects correctly. Covered by an automated @security test.
F-05 | Medium | Payment-reminder modal causes intermittent suite failures | Test framework / advertiser portal | The 'payment is due' modal renders over the dashboard on an unpredictable subset of loads and swallows clicks. Only one suite dismissed it, inline. | Dashboard tests failed intermittently on locators that were genuinely present, which reads as product flakiness. | Fixed - shared dismissal helper in utility/appActions.ts; Dashboard suite fix pending in section 3.
F-06 | Low | Management staging uses an untrusted internal certificate | Environment / config | management.stg.fusetwo.com presents a certificate issued by the internal FLEX-DC01 CA, which Chromium does not trust. | Any browser-based test against management staging fails at TLS. | Handled - TLS verification relaxed for the staging environment only, via IGNORE_HTTPS_ERRORS.
F-07 | High | Management tests were running against the IIS 401 page, not the portal | Management portal | The portal uses Windows Integrated Authentication: IIS answers the first request with 401 and WWW-Authenticate: Negotiate/NTLM, before the app loads. ManagementLoginPage looked for an e-mail/password form that never appears, found nothing, and returned silently. | Every management test was asserting against the '401 - Unauthorized' error page. Management was effectively unautomated. | Fixed - Chromium now single-signs-on with the Windows domain session (--auth-server-allowlist). Verified 401 -> 200 on dev and staging. CI needs the build service account granted portal access.
F-08 | Medium | Management spec asserts navigation that does not exist | Management portal - test correctness | testManagementReadOnly expects nav sections Dashboard, Advertisers, Accounting and Reports. The real portal nav is Advertiser (Overview, Revenue Report, Receivables Report, Advertiser Balance, Advertiser Reconciliation, Referred Publishers, Recruited Publishers, Promo Codes, Terms and Conditions, Advertiser Invoice) and Reports. | Three of the four asserted sections do not exist, so the test could not have been passing against the real portal. | Open - to be corrected as part of the management coverage work; see docs/management-automation.md.

## How To Run
How to run the suite
Any of these can be run locally or queued in the Azure pipeline.
Goal | Command | Notes
Full suite on dev | npm test | Default environment. Unchanged from before.
Full suite on staging | npm run test:staging | Targets advertiserstg.fusetwo.com.
Full suite on live | npm run test:prod | Data-mutating tests are excluded automatically.
Release gate (recommended) | npm run gate:staging | Blocker scenarios only. Run against every release candidate.
Release gate on live | npm run gate:prod | Read-only. Use after a deployment.
Check open defects | npm run known-bugs | Failures expected until each bug is fixed.
Allow writes on live (deliberate) | ALLOW_WRITE_TESTS=true npm run test:prod | Creates real advertiser data. Use with care.
Open the last HTML report | npm run report | Traces and screenshots for any failure.
Environments
Environment | Advertiser app | Management portal
dev (default) | advertiser.dev.fusetwo.com | management.dev.fusetwo.com
staging | advertiserstg.fusetwo.com | management.stg.fusetwo.com
live | advertiser.fusetwo.com | management.fusetwo.com
Tags: @blocker = must pass before release (the gate runs these) ¦ @crud = create/read/update/delete ¦ @smoke = fastest liveness signal ¦ @write = mutates real data, skipped on live ¦ @known-bug = guards an open defect, never gates a release.