## Executive Summary
FuseTwo QA — Master Report
Syed Shah · QA · fusetwo / Development
Consolidated view of my QA work from 17 July to 17 August 2026 — board sign-offs, bugs raised, staging re-verification, the FuseTwo.com website launch QA, and this week's advertiser-portal audit. Figures read from Azure DevOps.
153 | 108 | 67
Work items I own on the board | Tickets verified & signed off (17 Jul – 12 Aug) | Bugs I have raised — 29 fixed
20 | 14 | 9
Web-board items QA'd against the live site (13 Aug) | Bugs re-verified on staging (10 Aug) | New defects found this week (17 Aug)
Coverage
• Management / Control portal · Advertiser portal · Signup & Registration · Reporting · Programs, Campaigns, Creatives, Coupons & Products · Publishers · Accounting · Playwright automation suites · the FuseTwo.com marketing site.
Impact highlights
• Cleared the FuseTwo.com website launch: all nine page builds and the related bugs QA'd and signed off (13 Aug), including #297 which I had failed on 5 August.
• Caught the highest-risk defects on the board: a security bug exposing plaintext passwords (#682), two infinite-API-loop bugs that froze the portal (#680 / #690), and a signup-blocking HTTP 500 (#683).
• Ran repeated staging re-verification sweeps (10 & 12 Aug) — 14 board bugs re-tested and 42 QA-Ready/Doing tickets re-checked against staging.
• This week: full advertiser-portal audit across Programs, Publishers, Accounting and Reporting; every sales-value calculation I checked reconciled exactly. Logged 5 onboarding-audit bugs (#760–#764) and documented 4 more.
• Maintain 153 work items on the board and delivered the Playwright automation-suite tickets under Feature #64.
Top open risks
#682 Security (High, still New) — Resume API returns the account password and security answer in plaintext — highest-risk item open on the board.
#690 Infinite fetch loop (High, still New) — Advertiser Overview floods the UI with error toasts and freezes the page.
#760 Add-Program automation (High, new this week) — Website-extraction step hangs indefinitely, blocking self-serve program creation.
Creatives accept HTML / “script” (new this week) — Field rule not enforced; markup saves to the database — stored-content / XSS concern (in Bug Audit, pending logging).
#762 Pricing mismatch (new this week) — Advertiser agreement shows $50 monthly minimum vs $100 on the management Pricing Schedule — customer-facing.
Reporting (#726 + this week) — Performance Report still returns no data (Sales Summary now fixed, Performance not); “Publishers” count inflated on Reconcile Sales / Sales Summary.

## Activity by Workstream
QA activity by workstream — 17 July to 17 August 2026
Period | Workstream | Tested / verified | Bugs raised | Result / notes
17–31 Jul | Module regression & ticket sign-off (cumulative) | ≈ 60 | 32 | Steady sign-off across Advertiser Max, Reporting, Automation and Programs.
3 Aug | Regression + automation suites | 43 | — | 28 regression tickets plus 15 Playwright automation suites verified in one day.
10 Aug | Staging bug re-verification sweep | 14 | — | 7 still reproducible, 6 confirmed fixed, 1 could not be verified.
10–13 Aug | FuseTwo Development board (app / portal) | 14 → QA Ready | 15 | 2 Critical, 4 High (incl. security), 4 Medium, 4 Low, 1 removed.
12 Aug | Staging daily + Dharmendra re-verification | 40 scenarios / 42 tickets | 6 | Advertiser-portal & management filters, reporting, coupons; 42 QA-Ready/Doing tickets re-checked.
13 Aug | FuseTwo.com Web board (marketing site) | 20 | 0 | 16 verified to Done, 2 failed (#414 Services, #415 Verticals), 2 pending (#220, #222).
13 Aug | End-to-end sanity pass | 11 areas | 0 | Management portal (staging) + FuseTwo site — no new critical issues.
17 Aug | Advertiser-portal deep audit (staging) | 4 sections / ~22 screens | 9 | Programs, Publishers, Accounting, Reporting; sales-value calcs verified; 5 logged + 4 documented.
17 Aug | HubSpot e-mail-template tickets | 4 | — | 752 & 755 verified to Done; 754 & 756 failed re-test, returned to team.

## Bugs (Aug 10–17)
Bugs I raised & defects I found — 10 to 17 August
Severity as recorded on the ticket. Group C is documented in the Bug Audit, pending board logging.
Bug | Severity | Title | Area | Raised | State | Link
Group A — FuseTwo Development board, raised 10–12 August (15)
680 | Critical | Advertiser Overview — infinite API loop (219+ calls/min) | Advertiser Portal | 2026-08-10 | Done | Open in DevOps
690 | High | Advertiser Overview — infinite fetch/render loop floods UI, freezes page | Advertiser Portal | 2026-08-10 | New | Open in DevOps
681 | High (Security) | CAPTCHA not validated — wrong answer accepted | Signup | 2026-08-10 | Done | Open in DevOps
682 | High (Security) | Resume API returns plaintext password & security answer | Signup API | 2026-08-10 | New | Open in DevOps
683 | High | Save & Submit returns intermittent HTTP 500 — signup blocked | Signup | 2026-08-10 | Done | Open in DevOps
725 | High | Terms & Conditions page blank (GET /terms → HTTP 500) | Advertiser Portal | 2026-08-12 | New | Open in DevOps
684 | Medium | Advertiser Detail page shows 'Coming Soon' — 31 approvals blocked | Management | 2026-08-10 | New | Open in DevOps
723 | Medium | Search fails to find non-Approved advertisers under 'All Statuses' | Advertiser Portal | 2026-08-12 | New | Open in DevOps
726 | Medium | Sales Summary & Performance reports show no data while sales exist | Advertiser Portal | 2026-08-12 | New | Open in DevOps
727 | Medium | Editing a Coupon loads wrong Promotion Type, drops Coupon Code | Advertiser Portal | 2026-08-12 | New | Open in DevOps
685 | Low | Typo in security question — 'What Is your favorite book?' | Signup | 2026-08-10 | QA Ready | Open in DevOps
686 | Low | 'Required field*' helper text never hides after valid input | Signup | 2026-08-10 | Done | Open in DevOps
687 | Low | Dropdowns open upward, overlaying the fields above | Signup | 2026-08-10 | Committed | Open in DevOps
688 | Low | 'Commission Type' label renders in orange brand colour | Management | 2026-08-10 | Done | Open in DevOps
722 | Invalid | 'All Statuses' filter shows only 1 result (could not reproduce) | Advertiser Portal | 2026-08-12 | Removed | Open in DevOps
Group B — Onboarding audit, logged this week (17 Aug), assigned to Alex Buchanan (5)
760 | High | Add Program automation hangs indefinitely on 'Extracting website information' | Advertiser Portal | 2026-08-17 | New | Open in DevOps
761 | Medium | Default (auto-created) creatives cannot be edited — Edit action disabled | Advertiser Portal | 2026-08-17 | New | Open in DevOps
762 | Medium | Monthly minimum mismatch: agreement ($50) vs management Pricing Schedule ($100) | Advertiser / Mgmt | 2026-08-17 | New | Open in DevOps
763 | Low | Legacy 'affiliate network / The Network' terminology in advertiser agreement | Advertiser Portal | 2026-08-17 | New | Open in DevOps
764 | Low | Legacy 'FlexOffers.com' branding in management Pricing Schedule | Management | 2026-08-17 | New | Open in DevOps
Group C — Found in the advertiser-portal sweep, documented in the Bug Audit (17 Aug, pending logging) (4)
(pending) | High | HTML and the word 'script' accepted & saved in Creatives Text Link (rule not enforced) | Creatives | 2026-08-17 | To log | Bug Audit doc
(pending) | High | Performance Report returns no data for a period that has data (relates to #726) | Reporting | 2026-08-17 | To log | Bug Audit doc
(pending) | Medium | 'Publishers' count inflated on Reconcile Sales (6) & Sales Summary (9) for one publisher | Reporting | 2026-08-17 | To log | Bug Audit doc
(pending) | Medium | 'Maximum 150 characters' limit not enforced on Coupons & Offers text | Coupons & Offers | 2026-08-17 | To log | Bug Audit doc

## Bug Fix Status
Have my bugs actually been fixed? (all 67 bugs I've raised)
Snapshot read from Azure DevOps on 7 August 2026. 'Fixed' groups Done + QA Ready (a fix has been delivered).
Outcome | Count | % of 67 | What it means
Fixed & verified by me (Done) | 13 | 19% | Closed out — fix confirmed working.
Fixed, awaiting my verification (QA Ready) | 16 | 24% | Developer delivered a fix; in my test queue.
Being worked on (Committed) | 5 | 7% | Picked up, not delivered yet.
Never picked up (New) | 33 | 49% | No developer has started.
FIXED (verified or delivered) | 29 | 43% | Nearly half of everything I've raised has a fix in hand.
NOT FIXED | 38 | 57% | Still open — 5 of these have no assignee and cannot move.
Portfolio composition (153 work items I own)
Bugs I found by testing | 67 (44%)
Backlog items — Advertiser Max carry-over | 86 (56%)
Bugs raised — June / July / August | 16 / 47 / 3
Overall closed (Done) across 153 items | 20 (13%)

## Staging Verify (Aug 10)
Staging QA verification — 10 August 2026
14 board bugs re-tested on staging (advertiserstg / management.stg). 7 reproducible, 6 working fine, 1 could not verify.
Bug | Title | Staging result | Notes
#682 | API exposes plaintext password in response | Reproducible | Login response body contains the password field in plaintext.
#685 | Typo in security question — 'What Is your favorite book?' | Reproducible | Incorrect capitalisation of 'Is' in the dropdown.
#686 | 'Required field *' label stays visible after valid input | Reproducible | Company Name field — asterisk label persists.
#687 | Country dropdown opens upward, overlaying fields above | Reproducible | Dropdown direction overlays higher fields.
#688 | 'Commission Type' label renders in orange brand colour | Reproducible | Program Defaults tab — should be neutral.
#90 | Staging-specific regression (ADO #90) | Reproducible | Reproduced on staging; details in ADO.
#542 | Programs filter still visible with 0 programs | Reproducible | Fix #2 not on staging; Fix #3 (Tracking Diagnosis) working.
#683 | Advertiser signup form fails to load / blank page | Working Fine | Form loads correctly at /signup.
#690 | Advertiser Overview infinite API loop / error toasts | Working Fine | Page loads cleanly; no toasts (staging build).
#535 | Private program displayed as 'visible to everyone' | Working Fine | Program 249365 now shows 'Private' correctly.
#452 | Dark mode — readability / contrast in Publisher Portal | Working Fine | Headers and dropdowns readable in dark mode.
#574 | Advertiser detail — 'Failed to load notes' toasts | Working Fine | No error toasts; page loads cleanly.
#595 | Advertiser Details > Website URL overlaps section | Working Fine | URL truncated with ellipsis; no overlap.
#449 | Dark mode — selected row highlight on Daily Budget | Could Not Verify | No budget records in test account to trigger the state.

## Website QA (Aug 13)
FuseTwo.com Web board — QA against the live site (13 Aug)
20 'QA Ready' items tested. 16 verified to Done, 2 failed and returned, 2 still pending.
ID | Item | Result | Moved to | Notes
179 | Homepage final CTA text | PASS | Done | 'Let's Talk' present; 'Book A Call' removed
188 | Footer 'Sign Up' label | PASS | Done | Correct label; verified
189 | Footer TikTok icon | PASS | Done | TikTok present, no duplicate LinkedIn
190 | Footer 'Brands' sub-links | PASS | Done | Services & Industries present
191 | Footer 'Terms & Conditions' label | PASS | Done | Link intentionally hidden per dev
204 | Homepage build | PASS | Done | Fully built & responsive
205 | Platform page | PASS | Done | Hero, sections render
206 | About Us page | PASS | Done | Story + mission render
207 | Brands page | PASS | Done | Hero + sections render
208 | Publishers page | PASS | Done | Hero + CTAs render
209 | Privacy Policy page | PASS | Done | Real effective date Jul 15, 2026
210 | Terms & Conditions page | PASS | Done | Real dates shown
223 | T&C placeholder dates | PASS | Done | Real dates now shown
226 | Privacy placeholder dates | PASS | Done | Real dates now shown
297 | Header Log In/Sign Up dev links | PASS | Done | Links hidden; no dev-subdomain links
318 | Industries page | PASS | Done | Hero + verticals section render
414 | Services page | FAIL | Committed | Hero CTA, active-nav red, PNG not WebP, empty alt
415 | Verticals template page | FAIL | Committed | Bare default WordPress layout on production
220 | Cross-browser / responsive QA | Pending | QA Ready | Not yet verified
222 | Form validation styling | Pending | QA Ready | Not yet verified